## SIT Prep List
DRAFT
# | Module | Task | Comments | Due Date | Status | Owner
1 | MuleSoft Platform Setup | SIT env should be configured |  | 2020-12-18 | Complete | Haritha T
|  | Public Cert, Self-signed Cert and Client Cert should be configured in Non-Production DLB |  | 2020-12-18 | Complete | John B / Devon
|  | Share the Self-signed certificate with PwC team |  | 2020-12-16 | Complete | Brandon
|  | All Security Firewall Rule, URL mapping Rule etc are configured in VPC/DLB |  | 2020-12-18 | Complete | Ritwik
|  | Verify Developer has (Haritha G, Kevin) access to SIT environoment |  | 2020-12-18 | Complete | Haritha T
|  | Make sure the StingRay proxy API IP is whitelisted in Rackspace | For SIT testing, team agreed to use Dev proxy application. During the UAT testing, the proxy app will be deployed to UAT and new IP has to be whitelisted | 2020-12-18 | NA
2 | System Credentials | Verify Accuity IP address provided for whitelisting, public certificates for client cert validation | IP whitelisting & Two-way SSL will not be enabled for SIT testing since we are testing using Postman | 2020-12-18 | NA
|  | Verify Accuity SIT credentials | Agreed to test in Postman so, the connectivity with Accuity test system is not required for SIT testing | 2020-12-18 | NA
|  | Verify IBS SIT credentials | Username: Password: | 2020-12-18 | Complete | Haritha G
|  | Verify Maeve Db SIT credentials | Decision pending: on-prem vs azure maeve db - 12/18 Connection String | 2020-12-18 | Complete | Devon
|  | Verify Sting`Ray SIT credentials | appName: accountName: Username: Password: | 2020-12-18 | Complete | Devon
|  | Verify Azure Error / lookup Db credentials | Connection String | 2020-12-18 | Complete | Haritha T
Import 40M records to On-prem and Azure Maeve
3 | DevOps | Check-in the application code to gitlab in dev branch using Maven archetype |  | 2020-12-18 | Complete | Ritwik
|  | Confirm DevOps / CICD pipeline is configured accurately for SIT Deployment | gitlab --> nexus; Nexus --> Cloudhub | 2020-12-18 | Complete | Ritwik
|  | Verify the deployment properties like Mule worker Size , vCores and others are configured properly for each application in SIT |  | 2020-12-18 | Complete | Ritwik
|  | Make sure the gitlab repository is following standard naming conventions |  | 2020-12-18 | Complete | Ritwik
|  | Share the above details with Pat during the Dry run of SIT deployment | app properties, vCore size, number of workers.. | 2020-12-18 | Complete | Ritwik
4 | LogRhythm | Confirm LogRhythm is able to pull the Cloudhub logs for all SIT applications |  | 2020-01-04 | Complete | Devon
5 | Post Deployment Check | Verify all applications are running in Cloudhub |  | 2020-12-23 | Complete | Haritha T
|  | Confirm all API policies / alerts are active in Cloudhub |  | 2020-12-23 | Complete | Haritha T
|  | Verify if there is any confidential information (password) is visible in Cloudhub |  | 2020-12-23 | Complete | Haritha T
|  | During dry run of the each applications, make sure no NPPI data is logged in Cloudhub |  | 2020-12-23 | Complete | Haritha T
Make sure account type codes in lookup table are accurate with IBS
Confidential Information for the sole benefit and use of PwC's Client

## SIT Runbook
DRAFT
Task# | Task | Owner | Planned Start Date | Duration | Planned End Date | Dependency | Status
1 | Update the latest self signed certificate with in the applications | Ritwik | 2020-12-17 |  | 2020-12-17
2 | Unit test all the applications in your local environment | Ritwik | 2020-12-17 |  | 2020-12-18
3 | Check-in the code for the following applications to gitlab wsfs-accuity-experience-api wsfs-ibs-maeve-process-api wsfs-maeve-db-system-api wsfs-ibs-system-api wsfs-mulesoft-non-prod-proxy wsfs-azure-db-system-api | Ritwik | 2020-12-14 |  | 2020-12-18
4 | Update the details of application properties in gitlab | Ritwik | 2020-12-17 |  | 2020-12-18
5 | Deploy the code for the above applications to Nexus from Gitlab | Pat | 2020-12-21 |  | 2020-12-22
6 | Deploy the code for the above applications to Cloudhub from Nexus, make sure all propery values are configured for each application for SIT | Pat | 2020-12-21 |  | 2020-12-22
7 | Confirm the properties, vCores, worker size is deployed accurately for each application | Haritha | 2020-12-22 |  | 2020-12-22
8 | Confirm the latest DLB, self signed certificates, URL mapping in DLB | Haritha | 2020-12-18 |  | 2020-12-18
9 | Dry run the applications to confirm if the interface is working as expected | Haritha | 2020-12-18 |  | 2020-12-23
10 | Create postman collections for all the SIT scenarios | Haritha | 2020-12-16 |  | 2020-12-16
11 | Identify the test data / records in IBS | Devon | 2020-12-16 |  | 2020-12-24
12 | Create the test documents / data in Maeve Cosmos Db | Haritha | 2020-12-16 |  | 2020-12-24
13 | Make sure the look up values are matched with the account type values in IBS in Azure look up table | Devon | 2020-12-17 |  | 2020-12-17
Confidential Information for the sole benefit and use of PwC's Client

## UAT Prep List
DRAFT
# | Module | Task | Comments | Due Date | Status | Owner
1 | MuleSoft Platform Setup | UAT env should be configured in Anypoint
Public Cert, Self-signed Cert and Client Cert should be configured in Non-Production DLB
All Security Firewall Rule, URL mapping Rule etc are configured in VPC/DLB
Make sure the StingRay proxy API IP is whitelisted in Rackspace
2 | System Credentials | Verify Accuity IP address provided for whitelisting, public certificates for client cert validation | IP whitelisting & Two-way SSL will not be enabled for SIT testing since we are testing using Postman
|  | Verify Accuity SIT credentials | Agreed to test in Postman so, the connectivity with Accuity test system is not required for SIT testing
|  | Verify IBS SIT credentials | Username: Password:
|  | Verify Maeve Db SIT credentials | Decision pending: on-prem vs azure maeve db - 12/18 Connection String
|  | Verify Sting`Ray SIT credentials | appName: accountName: Username: Password:
|  | Verify Azure Error / lookup Db credentials | Connection String
Import 40M records to On-prem and Azure Maeve
3 | DevOps | Check-in the application code to gitlab in dev branch using Maven archetype
|  | Confirm DevOps / CICD pipeline is configured accurately for SIT Deployment | gitlab --> nexus; Nexus --> Cloudhub
Verify the deployment properties like Mule worker Size , vCores and others are configured properly for each application in SIT
Make sure the gitlab repository is following standard naming conventions
|  | Share the above details with Pat during the Dry run of SIT deployment | app properties, vCore size, number of workers..
4 | LogRhythm | Confirm LogRhythm is able to pull the Cloudhub logs for all SIT applications
5 | Post Deployment Check | Verify all applications are running in Cloudhub
Confirm all API policies / alerts are active in Cloudhub
Verify if there is any confidential information (password) is visible in Cloudhub
During dry run of the each applications, make sure no NPPI data is logged in Cloudhub
Make sure account type codes in lookup table are accurate with IBS
Confidential Information for the sole benefit and use of PwC's Client

## UAT Runbook
DRAFT
Task# | Task | Owner | Completed Date | Status
1 | Update CICD pipeline to reflect dev, test, master branches, snapshot version | Pat | 2021-03-19 | Complete
2 | Create UAT pipeline for all the apps | Haritha T/G | 2021-03-19 | Complete
3 | Complete SIT Testing and approval to deploy the code to UAT | Devon | 2021-03-15 | Complete
4 | CAB approval for UAT deployment | Chris | 2021-03-16 | Complete
5 | Load legacy data from SQL to Mongo Db | Kevin | 2021-03-23 | Complete
6 | Load legacy data to Maeve Cosmos Db | Kevin | 2021-03-25 | Complete
7 | Get Stingray UAT connectivity details | Haritha T | 2021-03-15 | Complete
8 | Update the deploy, gitlab-ci.yml scripts for wsfs-stingray-system-api in gitlab | Haritha T | 2021-03-16 | Complete
9 | Update the configuration in UAT Properties (Test branch) in gitlab | Haritha T | 2021-03-16 | Complete
10 | Deploy wsfs-nonprod-proxy-api to UAT and enable static ips for this application | Haritha T | 2021-03-17 | Complete
11 | Send the Ips to Rackspace/Azure to whitelist them | Chris | 2021-03-17 | Complete
12 | Whitelist UAT Stingray system API IP in Rackspace; Test the connectivity after whitelisting | Haritha T | 2021-03-23 | Complete
13 | Update the deploy, gitlab-ci.yml scripts for wsfs-ibs-maeve-process-api in gitlab | Haritha T | 2021-03-17 | Complete
14 | Update the configuration in UAT Properties for ibs-maeve-process-api; Merge to Test branch in gitlab | Haritha T | 2021-03-17 | Complete
15 | Run the UAT pipeline and Deploy wsfs-ibs-maeve-process-api to Cloudhub UAT | Haritha T | 2021-03-24 | Complete
16 | Get Maeve db UAT connectivity details | Haritha T | 2021-03-17 | Complete
17 | Update the deploy, gitlab-ci.yml scripts for wsfs-maeve-db-system-api in gitlab | Haritha T | 2021-03-17 | Complete
18 | Update the configuration in UAT Properties for maeve-db-sys-api; Merge the code from dev to Test branch in gitlab | Haritha T | 2021-03-17 | Complete
19 | Deploy wsfs-maevedb-system-api to UAT Cloudhub | Haritha T | 2021-03-17 | Complete
20 | Enable static Ips and whitelist the IPs in Azure | Chris/Mark | 2021-03-17 | Complete
21 | Test the connectivity with UAT maeve db after whitelisting | Haritha T | 2021-03-23 | Complete
22 | Get Error, lookup db UAT connectivity details | Haritha T | 2021-03-24 | Complete
23 | Update the deploy, gitlab-ci.yml scripts for wsfs-azure-db-system-api in gitlab | Haritha T | 2021-03-17 | Complete
24 | Update the configuration in UAT Properties; Merge to Test branch in gitlab | Haritha T | 2021-03-24 | Complete
25 | Deploy wsfs-azuredb-system-api to UAT Cloudhub | Haritha T | 2021-03-24 | Complete
26 | Enable static Ips and whitelist the IPs in Azure | Chris/Mark | 2021-03-17 | Complete
27 | Test the connectivity with UAT azure db after whitelisting | Haritha T | 2021-03-23 | Complete
28 | Update the deploy, gitlab-ci.yml scripts for wsfs-system-availability-exp-api | Haritha T | 2021-03-17 | Complete
29 | Update the configuration in UAT Properties for system-availability-api; Merge the code from dev to Test branch in gitlab | Haritha T | 2021-03-17 | Complete
30 | Deploy wsfs-system-availability-api to UAT Cloudhub | Haritha T | 2021-03-17 | Complete
31 | Test the connectivity by running the API in postman | Haritha T | 2021-03-17 | Complete
32 | Update the config in Test branch and Deploy wsfs-accuity-experience-api to UAT Cloudhub | Haritha T | 2021-03-17 | Complete
33 | Update the config in Test branch and Deploy wsfs-notification-system-api to UAT Cloudhub | Haritha T | 2021-03-18 | Complete
34 | Get IBS UAT connectivity details; a. Update cert in key store and trust store | Haritha T/G | 2021-03-24 | Complete
35 | Update the configuration in UAT Properties (Test branch) in gitlab | Haritha T/G | 2021-03-24 | Complete
36 | Deploy wsfs-ibs-customer-system-api to UAT | Haritha T/G | 2021-03-24 | Complete
37 | Make sure the UAT platform is configured with API Manager, DLB certs and other components | Haritha T/G | 2021-03-24 | Complete
38 | Dry run the accuity interface in UAT | Haritha T/G | 2021-03-24 | Complete
39 | Validate that no NPPI data is being logged to cloudhub before making the first UAT API call | Haritha T/G/Devon | 2021-03-24 | Complete
Confidential Information for the sole benefit and use of PwC's Client

## Prod Runbook
Task ID | Production Deployment - Tasks | Owner | Complete Date | Status | Comments | Dependency | Key Milestone | WSFS Resource Requirements
1 | Update CICD pipeline to reflect dev, test, master branches, snapshot version | Pat | 2021-04-20 | Complete
2 | Create Prod pipeline for all the apps | Haritha T/Robel | 2021-04-20 | Complete
3 | Complete UAT Testing and accuity approval to deploy the code to UAT | Devon | 2021-04-20 | Complete
4 | CAB approval for Prod deployment | Chris | 2021-04-20 | Complete
5 | Complete loading legacy data from SQL to UAT Maeve Db | Devon/Robert | 2021-04-20 | Complete
6 | Complete loading data from UAT Maeve db to Prod Maeve Db | Devon/Robert | 2021-04-20 | Complete
7 | Deploy the accuity-exp-api to Production to test the connectivity with Accuity | Haritha T | 2021-04-20 | Complete
8 | use different secure.key and encrypt the properties in Production | Haritha T | 2021-04-20 | Complete
9 | Create a diff Prod instance in API Manager and update api_id in gitlab properties | Haritha T | 2021-04-20 | Complete
10 | Update the gitlab-ci.yml scripts (template) for wsfs-stingray-system-api in gitlab | Haritha T | 2021-04-20 | Complete
11 | Update the configuration in Prod Properties (dev branch) in gitlab and merge to Test, Master branches | Haritha T | 2021-04-20 | Complete
12 | Deploy wsfs-nonprod-proxy-api to Prod and enable static ips for this application | Haritha T | 2021-04-20 | Complete
13 | Send the Ips to Rackspace/Azure to whitelist them | Chris | 2021-04-20 | Complete
14 | Whitelist Prod Stingray system API IP in Rackspace; Test the connectivity after whitelisting | Haritha T | 2021-04-20 | Complete
15 | Update the gitlab-ci.yml scripts (template) for wsfs-ibs-maeve-process-api in gitlab | Haritha T | 2021-04-20 | Complete
16 | Update the configuration in Prod Properties for ibs-maeve-process-api; Merge to Test, master branch in gitlab | Haritha T | 2021-04-20 | Complete
17 | Run the Prod pipeline and Deploy wsfs-ibs-maeve-process-api to Cloudhub Prod | Haritha T | 2021-04-20 | Complete
18 | Get Maeve db Prod connectivity details | Devon S | 2021-04-20 | Complete
19 | Update the gitlab-ci.yml scripts (template) for wsfs-maeve-db-system-api in gitlab | Haritha T | 2021-04-20 | Complete
20 | Update the configuration in Prod Properties for maeve-db-sys-api; Merge the code from dev to Test, master branch in gitlab | Haritha T | 2021-04-20 | Complete
21 | Deploy wsfs-maevedb-system-api to Prod Cloudhub | Haritha T | 2021-04-20 | Complete
22 | Enable static Ips and whitelist the IPs in Azure | Chris/Mark | 2021-04-20 | Complete
23 | Test the connectivity with Prod maeve db after whitelisting | Haritha T | 2021-04-20 | Complete
24 | Get Error, lookup db Prod connectivity details | Devon | 2021-04-20 | Complete
25 | Update the gitlab-ci.yml scripts for wsfs-azure-db-system-api in gitlab | Haritha T | 2021-04-20 | Complete
26 | Update the configuration in Prod Properties; Merge to Test, master branch in gitlab | Haritha T | 2021-04-20 | Complete
27 | Deploy wsfs-azuredb-system-api to Prod Cloudhub | Haritha T | 2021-04-20 | Complete
28 | Enable static Ips and whitelist the IPs in Azure | Chris/Mark | 2021-04-20 | Complete
29 | Test the connectivity with Prod azure db after whitelisting | Haritha T | 2021-04-20 | Complete
30 | Update the gitlab-ci.yml scripts for wsfs-system-availability-exp-api | Haritha T | 2021-04-20 | Complete
31 | Update the configuration in Prod Properties for system-availability-api; Merge the code from dev to Test, master branch in gitlab | Haritha T | 2021-04-20 | Complete
32 | Deploy wsfs-system-availability-api to Prod Cloudhub | Haritha T | 2021-04-20 | Complete
33 | Test the connectivity by running the API in postman | Haritha T | 2021-04-20 | Complete
34 | Update the config in Test branch and Deploy wsfs-accuity-experience-api to Prod Cloudhub | Haritha T | 2021-04-20 | Complete
35 | Update the config in dev branch, merge to Test, master branches and Deploy wsfs-notification-system-api to Prod Cloudhub | Haritha T | 2021-04-20 | Complete
36 | Get IBS Prod connectivity details; a. Update cert in key store and trust store | Devon | 2021-04-20 | Complete
37 | Update the configuration in Prod Properties (Dev branch); merge to Test, Master branches in gitlab | Haritha T | 2021-04-20 | Complete
38 | Deploy wsfs-ibs-customer-system-api to Prod | Haritha T | 2021-04-20 | Complete
39 | Deploy wsfs-encryption-api to Prod | Haritha T | 2021-04-20 | Complete
40 | Make sure the Prod platform is configured with API Manager, DLB certs and other components | Haritha T | 2021-04-21 | Complete
41 | Dry run the accuity interface in Prod | Devon | 2021-04-21 | Complete
42 | Validate that no NPPI data is being logged to cloudhub before making the first Prod API call | Haritha T/Devon | 2021-04-21 | Complete
Confidential Information for the sole benefit and use of PwC's Client
Our Services were performed and this Deliverable was prepared for the sole use and benefit of, and pursuant to a client relationship exclusively with, WSFS ("Client"). PwC is providing no opinion, attestation or other form of assurance and disclaims any contractual or other responsibility to others based on their access to or use of the Deliverable. Accordingly, the information in this Deliverable may not be relied upon by anyone other than Client

## Contacts
DRAFT
Department/Team | Name
Mobile
WSFS | Devon Smith
Haritha G
Kevin Marek
PWC
| Dhirendra Tiwari | 980-226-3147
| Ritwik Roy | 860-989-9227
| Haritha Thokala | 805-975-3846
All resources working from home should verify Remote Access prior to commencement of tasks.
Confidential Information for the sole benefit and use of PwC's Client

## Approval
DRAFT
5.0 Approval
IMPORTANT: An embedded approval indicates that the EIP Project Owner has reviewed and verified this Implementation Plan for accuracy, completeness, and the availability of qualified resources to perform the work as described.
EIP Project Owner | Embedded approval e-mail
Confidential Information for the sole benefit and use of PwC's Client

## Sheet1
DRAFT
APIs | Description
Accuity-experience-api | Experience API for Accuity interface
ibs-maeve-process-api | Process API for Accuity interface
maeve-db-system-api | System API for Maeve Db
ibs-system-api | System API for IBS
azure-db-system-api | System API for lookup table & to log Errors in Db
Confidential Information for the sole benefit and use of PwC's Client
Our Services were performed and this Deliverable was prepared for the sole use and benefit of, and pursuant to a client relationship exclusively with, WSFS ("Client"). PwC is providing no opinion, attestation or other form of assurance and disclaims any contractual or other responsibility to others based on their access to or use of the Deliverable. Accordingly, the information in this Deliverable may not be relied upon by anyone other than Client